## Gantt
Create a Gantt Chart in this worksheet. Enter title of this project in cell B1. Legend title is in cell I1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. |  | Overdose Fatality Review
Enter Company Name in cell B2. A legend is in cells I2 through AC2. |  | EXAMPLE County
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell F3 or allow the sample formula to find the smallest date value from the Gantt Data table. Project Start Date: label is in cell D3. |  |  | Project Coordinator: |  |  | Project Start Date: | 2021-01-04
A Scrolling Increment is in cell F4. Months for the dates in row 5 are displayed starting in cells I4 through cell BL4. Do not modify these cells. They are auto updated based on the project start date in cell F3. |  |  | Facilitator: |  |  | Show Schedule Starting at Day | 0 |  | January | [27 empty] | February
Cells I5 through BL5 contain the day number of the month for the Month represented in the cell block above each date cell and are auto calculated. Do not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. |  |  | Data Manager: | time axis 2021-01-04 to 2021-02-28
A scrollbar is in cells I6 through BL6. The increment for paging through the data is defined as 2 pages at a time and can be configured in the settings for the control bar. To jump forward or backward in the timeline, enter a value of 0 or higher in cell F4. A value of 0 takes you to the beginning of the chart.
This row contains headers for the project schedule that follows below them. Navigate from B7 through BL7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I7 and continues through cell BL7. All project timeline charting is auto generated based on the category, start date and number of days entered in the Milestones table. | Category | Task/Milestone Description | OFR Guide | Assigned To | Comments | Progress | Start | No. of Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. |  | OFR Orientation
|  | Review Module 1: OFR Member Recruitment | pp. 4–12 | Facilitator, Coordinator | More on this module at the COSSAP OFR website: https://www.cossapresources.org/Tools/OFR/Recruit | 100% | 2021-01-04 | 1
|  | Review Module 2: Planning OFR Meetings | pp. 13–18 | Facilitator, Coordinator | More on this module at the COSSAP OFR website: https://www.cossapresources.org/Tools/OFR/Plan | 100% | 2021-01-05 | 1
|  | Review Module 3: Facilitating OFR Meetings | pp. 19–27 | Facilitator, Coordinator | More on this module at the COSSAP OFR website: https://www.cossapresources.org/Tools/OFR/Facilitate | 100% | 2021-01-06 | 1
|  | Review Module 4: Collecting Data | pp. 28–31 | Facilitator, Coordinator, Data Manager | More on this module at the COSSAP OFR website: https://www.cossapresources.org/Tools/OFR/Collect | 0% | 2021-01-08 | 1
|  | Review Module 5: Building a Recommendation Plan | pp. 33–37 | Facilitator, Coordinator, Data Manager | More on this module at the COSSAP OFR website: https://www.cossapresources.org/Tools/OFR/Build | 0% | 2021-01-12 | 1
OFR Initial Planning
|  | Identify “governing committee” | p. 12 | Coordinator | Do we have a local coalition/task force that is a good fit? |  | 2021-01-04 | 2
|  | Identify coordinator, facilitator, and data manager roles | pp. 8–11 | Coordinator | Are these different individuals? Do we need to hire someone? | 60% | 2021-01-04 | 2
|  | Get county council approval |  | Coordinator | County council meets the second Tuesday |  | 2021-01-12 | 1
|  | Register as an OFR pilot site for access to technical assistance/community of practice |  | Coordinator | Register as an OFR pilot site: http://s.iir.com/OFRREDCap_Registration Place training and technical assistance request: https://www.cossapresources.org/Program/TTA | 50% | 2021-01-12 | 4
|  | Secure access to the REDCap database | p. 31 | Data Manager | https://projectredcap.org/partners/join/ It takes us a maximum of three weeks to process a license request, from the time of submission. It then takes us a maximum of two additional weeks to subsequently create accounts on the internal website where your organization's IT staff can download REDCap and begin installation. |  | 2021-01-15 | 35
|  | Establish interagency data sharing and confidentiality agreements | pp. 56–58 | Coordinator, Data Manager | Is state legislation in place? Are data sharing/confidentiality agreements in place for other types of fatality review? Consult legal counsel, as needed. |  | 2021-01-15 | 21
|  | Secure HIPAA compliant virtual platform, if virtual |  | Coordinator | Examples: WebEx Medical, Starleaf, GoToMeeting |  | 2021-01-22 | 7
|  | Review the list of suggested OFR participants, identify potential candidates, draft letter | p. 6, p. 40 | Coordinator, Facilitator | Preparatory work before doing outreach | 50% | 2021-01-29 | 5
|  | Recruit OFR members (follow-up emails and phone calls) | pp. 5–6 | Facilitator | This could take several weeks depending on number of members (typically 15–35) |  | 2021-02-05 | 14
|  | Collect signed data sharing and confidentiality agreements | pp. 29–30 | Coordinator, Data Manager | After members agree to participate, send a copy of the agreement. Send a reminder email to those who have not returned it. |  | 2021-02-19 | 7
|  | Review data and determine case selection criteria |  | Coordinator, Data Manager | We can't review every single death case. Are there specific topics to focus on? |  | 2021-02-19 | 3
|  | Develop protocol for secure data access/OFR records |  | Data Manager | Review considerations in this resource: https://www.cossapresources.org/Content/Documents/BriefingSheets/OFR_Practitioners_Guide_Appendice_Template_OFR_Data_Sharing_Protocol.pdf |  | 2021-02-22 | 7
|  | Provide orientation/training to each member |  | Facilitator | It is suggested to try to meet with all partners individually. Should an “orientation” zoom session be held before the first actual meeting? |  | 2021-02-26 | 14
|  | Set a meeting schedule |  | Coordinator | Consider holidays and other big events involving stakeholders |  | 2021-03-05 | 3
Meeting Preparation
|  | Select cases and email out to participants (two months prior) | p. 15 | Coordinator | Two to four examples from across 2020, especially those that have something to learn from them (good examples for first OFR) |  | 2021-03-01 | 5
|  | Invite guest members based on cases (six weeks prior) | p. 15 | Coordinator, Facilitator | Guests may be from agencies that provide services to individuals in review cases or serve similar individuals; could be identified from a coroner’s report. Make sure that they also sign a confidentiality agreement. |  | 2021-03-24 | 5
|  | Request case information from participants (one month prior) | p. 16 | Coordinator | Use template, send via encrypted email |  | 2021-04-05 | 1
|  | Reminder email, connect with key data providers (two weeks prior) | p. 16 | Coordinator | Outreach to remind about the meeting date, any other questions |  | 2021-04-21 | 2
|  | Summarize case, do additional research (two weeks prior) | p. 16 | Coordinator | Additional research not provided by OFR members may be social media, obituaries, media coverage |  | 2021-04-21 | 7
|  | Document progress on recommendations (two weeks prior) | p. 16 | Coordinator | Not applicable for the first meeting because no recommendations have been made |  | 2021-04-21 | 7
|  | Draft agenda and print meeting materials (one week prior) | p. 21, p. 44 | Coordinator | Plan for 90–120 minutes; open with general updates from participants and review ground rules |  | 2021-04-28 | 7
Meeting and Follow-Up
|  | Hold meeting | pp. 19–27 | Facilitator | Coordinator typically takes notes |  | 2021-05-05 | 1
|  | Prepare meeting minutes and send | p. 53 | Coordinator | Securely store minutes with case records |  | 2021-05-06 | 1
|  | Capture case information in database | p. 31 | Data Manager | Team meeting details and decedent case information |  | 2021-05-06 | 7
|  | Document recommendations in database and work on follow-up activities | p. 37 | Data Manager | Coordinator may need to reach out to subcommittee leads, if not involved directly |  | 2021-05-06 | 14
|  | Draft updates and reports to governing committee | p. 27 | Data Manager, Coordinator | Could be short summary or presentation/report |  | 2021-05-20 | 21
|  | Present updates to governing committee | p. 27 | Coordinator | Depends on OFR and governing committee structure; could be quarterly or annually |  | 2021-06-10 | 1
This is an empty row
This row marks the end of the Gantt milestone data. DO NOT enter anything in this row. To add more items, insert new rows above this one. |  | To add more data, insert new rows ABOVE this one
Note on F29: Author: Should the schedule be set before the member orientation, or after speaking with all of them and getting information about best times/ potential conflicts?

## How To
About This Template
Overview
Overdose Fatality Review (OFR) is a convening of multidisciplinary teams to review a decedent’s history and facilitate deeper understanding of missed opportunities for prevention and intervention that may have prevented an overdose death. The timeline for implementing an OFR depends on several factors, including staff and other resources to support planning and implementation as well as legislation in the state. The template provides a simple way to create a project management Gantt chart to help visualize and track implementation of an OFR. This tool will help you map out a realistic time frame for implementing your OFR and assist your team with working together to complete tasks within the timeline expected. The tool will be most helpful for planning and initiating your first OFR but can continue to be maintained for ongoing OFR implementation.
Navigating the Tool
Typical tasks are already listed for you in Column C, with a page reference to Overdose Fatality Review: A Practitioner’s Guide to Implementation where applicable in column D. Tasks are categorized into four phases: orientation to OFR, initial planning, meeting preparation, and meeting and follow-up. OFR resources that are typically involved in each task are listed as “assigned to” the task in column F. The example in the template starts in January 2021, so the dates flow from this time frame in column H. Each task is given a realistic target number of days in column I. The sample has suggested days based on an example implementation. Some tasks happen in sequence, while others can progress simultaneously. The calendar starting at column K will show a gray bar that corresponds to the date and time span for the task from columns H and I. You can use the scroll bar in line six to move forward and backward in the calendar. You can also change the number in cell H5 to jump to a specific day in the project timeline (e.g., if you want to view the calendar for the second month of implementation, you could enter Day “60”). Your OFR team can use column G to track progress on tasks by entering estimated percent completion. For example, if you’ve recruited 10 out of the 20 anticipated OFR members, you could enter “50%” for that task to show it is halfway complete.
Using the Tool for Your OFR Implementation
It is recommended to have a session where your OFR team works together to update the project management template.
1) Background: Enter your county name in cell B2 and the names of staff members serving in the project coordinator, facilitator, and data manager roles in cells D3–D5.
2) Project Start Date: In cell G3, enter the date that you begin the activities to plan for an OFR (not the date you aim to hold your first meeting). You will notice that some of the task dates in column H will automatically adjust based on your project start date.
3) Tasks: Review the list of tasks in Column C. Do you need to add anything, like seeking approval from the county council? Insert new tasks by inserting additional rows where needed. Is a task already complete, like securing the RedCap database? Enter 100% in the progress column. Is a task not relevant? Delete the line.
4) Assigned to: When you have identified the OFR staff resources, you can replace the role names “Facilitator,” “Coordinator,” and “Data Manager” in column E with their names and add others, as needed.
5) Comments: You can use column F to make notes about considerations you don’t want to forget.
6) Timeline: Go through each task and consider whether you need to adapt the dates in column H. Will it take you longer to have legal staff members review data sharing and confidentiality statements? You can change the number of days in column I.
· Working backwards: Some OFRs may be working towards a target implementation date based on grant requirements or other directives. You can enter the target date in cell H38 for the “hold meeting” task. Some dates in the schedule will auto-update (e.g., selecting cases two months prior). You can work backwards from that date to adjust the dates and time spans, but if you realize the time frame will not be realistic, you may need to push out your start date.
· Working forward: Your team may be starting with no end date in mind. In this case, continue working down the schedule to consider whether the timing of each task fits your local context or needs to be adjusted.
7) Check your work: When you have finished updating the template, use the scroll bar in line six to review the timeline and update any errors, like large gaps in the schedule or tasks that have gotten out of sequence.
8) Share your work: Once your schedule flows smoothly, if your OFR team has worked together to complete the template, then the final product should represent an agreed-upon timeline for implementation. You should share this template with other stakeholders, perhaps with your governing committee, so everyone has shared expectations for the timeline.
Your team may find it helpful to touch base weekly to update progress and review upcoming tasks and deadlines. If you have gotten behind, you can adjust the schedule, if needed, to move out your expected first meeting date.
More resources on OFR implementation are available at the COSSAP OFR website: https://www.cossapresources.org/Tools/OFR.
For additional support on this and other OFR resources, complete a technical assistance request at: https://www.cossapresources.org/Program/TTA.